## 📊 Overview
CAR RENTAL MANAGEMENT SYSTEM
Development Roadmap & Checklist
Created: 2025-11-18
PROJECT INFORMATION
Total Tables: | 35 tables | Full Premium Edition
Total Phases: | 5 phases | 16 weeks
Core Business: | 20 tables | Week 1-4
SEO & Content: | 5 tables | Week 5-6
Marketing & CRM: | 6 tables | Week 7-10
Enterprise: | 6 tables | Week 11-14
Testing & Deploy: | All | Week 15-16
Estimated Budget: | 500M - 1B VND
Team Size: | 3-5 people | Full-stack developers
Target Revenue: | 400-600M VND | Product sale price
OVERALL PROGRESS
Phase | Status | Tasks | Completed | Progress % | Duration
Phase 1: Database | Not Started | 45 | 0 | 0% | 4 weeks
Phase 2: Backend API | Not Started | 38 | 0 | 0% | 4 weeks
Phase 3: Frontend | Not Started | 32 | 0 | 0% | 4 weeks
Phase 4: Testing | Not Started | 15 | 0 | 0% | 1 week
Phase 5: Deployment | Not Started | 10 | 0 | 0% | 1 week

## Sheet1
testcase
T01 | Login | Nhập đúng username | TRUE
|  | nhap | flase
|  | %^^ | nhận không
|  | invaliad | flase

## 📅 Timeline
PROJECT TIMELINE - 16 WEEKS
Week | Dates | Phase | Focus Area | Key Deliverables | Status
Week 1 | 11/18 - 11/24 | Phase 1 | Database Design | ERD Review, SQL Scripts for Core tables | ☐
Week 2 | 11/25 - 12/01 | Phase 1 | Database Creation | Create DB, Indexes, Sample Data | ☐
Week 3 | 12/02 - 12/08 | Phase 1 | SEO Tables | Blog, Page, Review tables | ☐
Week 4 | 12/09 - 12/15 | Phase 1 | Advanced Tables | Marketing, CRM, Enterprise tables | ☐
Week 5 | 12/16 - 12/22 | Phase 2 | API Setup | Project setup, Auth, Core CRUD | ☐
Week 6 | 12/23 - 12/29 | Phase 2 | Business Logic | Booking flow, Payment integration | ☐
Week 7 | 12/30 - 01/05 | Phase 2 | SEO APIs | Blog, Review, SEO endpoints | ☐
Week 8 | 01/06 - 01/12 | Phase 2 | Advanced APIs | Marketing, Loyalty, Multi-tenant | ☐
Week 9 | 01/13 - 01/19 | Phase 3 | Admin Dashboard | Layout, Vehicle management | ☐
Week 10 | 01/20 - 01/26 | Phase 3 | Booking System | Customer booking flow | ☐
Week 11 | 01/27 - 02/02 | Phase 3 | Customer Portal | Profile, History, Reviews | ☐
Week 12 | 02/03 - 02/09 | Phase 3 | Advanced Features | Marketing, Loyalty UI | ☐
Week 13 | 02/10 - 02/16 | Phase 4 | Testing | Unit tests, Integration tests | ☐
Week 14 | 02/17 - 02/23 | Phase 4 | Testing | E2E tests, Performance tests | ☐
Week 15 | 02/24 - 03/02 | Phase 5 | Deployment | Staging deploy, Documentation | ☐
Week 16 | 03/03 - 03/09 | Phase 5 | Launch | Production deploy, Monitoring | ☐

## 🗄️ Phase 1 Database
PHASE 1: DATABASE DEVELOPMENT
Duration: 4 weeks ¦ Tables: 35
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | DB-001 | Review ERD | Review 35 tables ERD in dbdiagram.io | High | 4 | W1 | - | Use dbdiagram.io
☐ | DB-002 | Export SQL | Export MySQL/PostgreSQL scripts | High | 2 | W1 | DB-001 | Choose DB engine
☐ | DB-003 | Create Database | CREATE DATABASE car_rental_db | High | 1 | W1 | DB-002 | Setup credentials
☐ | DB-004 | Core Tables (20) | Create 20 core business tables | High | 8 | W1 | DB-003 | Vehicle, Customer, Booking...
☐ | DB-005 | Primary Keys | Add all PRIMARY KEY constraints | High | 2 | W1 | DB-004 | Check uniqueness
☐ | DB-006 | Foreign Keys | Add all FOREIGN KEY constraints | High | 4 | W1 | DB-005 | Test relationships
☐ | DB-007 | Indexes - Basic | Create indexes for frequently queried columns | High | 4 | W2 | DB-006 | CustomerID, VehicleID, BookingID
☐ | DB-008 | Indexes - SEO | Create indexes for Slug columns | Medium | 2 | W2 | DB-007 | Vehicle.Slug, BlogPost.Slug
☐ | DB-009 | Sample Data - Core | Insert sample data for core tables | High | 8 | W2 | DB-007 | 10 vehicles, 20 customers
☐ | DB-010 | Test Relationships | Test all FK relationships work | High | 4 | W2 | DB-009 | Try INSERT/UPDATE/DELETE
☐ | DB-011 | Backup Strategy | Setup automated backup | Medium | 3 | W2 | DB-009 | Daily backup script
☐ | DB-012 | SEO Tables (5) | Create BlogPost, BlogCategory, Page, Review, SeoRedirect | High | 4 | W3 | DB-006 | Content marketing tables
☐ | DB-013 | Update Vehicle | Add SEO fields to Vehicle table | High | 2 | W3 | DB-012 | Slug, MetaTitle, MetaDescription
☐ | DB-014 | Update VehicleCategory | Add SEO fields to VehicleCategory | High | 2 | W3 | DB-012 | Slug, MetaTitle, SeoContent
☐ | DB-015 | Update Branch | Add Local SEO fields to Branch | Medium | 2 | W3 | DB-012 | Latitude, Longitude
☐ | DB-016 | Sample Data - SEO | Insert sample blogs and reviews | Medium | 4 | W3 | DB-015 | 20 blog posts, 50 reviews
☐ | DB-017 | SEO Indexes | Create full-text search indexes | Medium | 2 | W3 | DB-016 | BlogPost.Content, Review.Content
☐ | DB-018 | Marketing Tables (6) | Notification, Template, Segment, Campaign, Loyalty | High | 4 | W4 | DB-006 | CRM features
☐ | DB-019 | Enterprise Tables (6) | Tenant, Plan, PricingRule, Corporate, Partner, Config | High | 4 | W4 | DB-006 | Multi-tenant ready
☐ | DB-020 | Update Customer | Add Loyalty fields to Customer | Medium | 1 | W4 | DB-018 | LoyaltyPoints, MembershipTier
☐ | DB-021 | Sample Data - All | Insert sample data for all tables | Medium | 6 | W4 | DB-020 | Complete sample dataset
☐ | DB-022 | Views - Reports | Create database views for common queries | Medium | 4 | W4 | DB-021 | Booking summary, Revenue
☐ | DB-023 | Stored Procedures | Create SPs for complex operations | Low | 4 | W4 | DB-021 | CalculateLoyaltyPoints, etc
☐ | DB-024 | Triggers | Create triggers for audit logging | Medium | 3 | W4 | DB-021 | Auto log changes
☐ | DB-025 | Performance Test | Test with 10k records | High | 4 | W4 | DB-024 | Check query performance
☐ | DB-026 | DB Documentation | Document all tables, relationships | Medium | 3 | W4 | DB-025 | ERD + Data dictionary
☐ | DB-027 | DB Optimization | Optimize slow queries | Medium | 3 | W4 | DB-025 | Add indexes, rewrite queries

## ⚙️ Phase 2 Backend
PHASE 2: BACKEND API DEVELOPMENT
Duration: 4 weeks ¦ Tech: Node.js/Java/Python
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | BE-001 | Project Setup | Initialize backend project (Node.js/Spring Boot) | High | 4 | W5 | DB-027 | Choose framework
☐ | BE-002 | Database Connection | Setup DB connection pool | High | 2 | W5 | BE-001 | Test connection
☐ | BE-003 | ORM Setup | Configure ORM (Sequelize/Hibernate/SQLAlchemy) | High | 4 | W5 | BE-002 | Map all 35 tables
☐ | BE-004 | Models - Core | Create models for 20 core tables | High | 8 | W5 | BE-003 | Vehicle, Customer, Booking
☐ | BE-005 | Auth System | JWT authentication, password hashing | High | 6 | W5 | BE-001 | bcrypt, jsonwebtoken
☐ | BE-006 | RBAC | Role-based access control (Admin/Staff/Customer) | High | 4 | W5 | BE-005 | Middleware
☐ | BE-007 | API - Vehicle | CRUD endpoints for Vehicle | High | 4 | W5 | BE-004 | GET, POST, PUT, DELETE
☐ | BE-008 | API - Customer | CRUD endpoints for Customer | High | 3 | W5 | BE-004 | With validation
☐ | BE-009 | API - Booking | Booking endpoints (create, update, cancel) | High | 6 | W6 | BE-008 | Complex business logic
☐ | BE-010 | Booking Validation | Check vehicle availability | High | 4 | W6 | BE-009 | Date overlap check
☐ | BE-011 | API - Invoice | Invoice generation endpoints | High | 4 | W6 | BE-009 | Calculate total
☐ | BE-012 | API - Payment | Payment processing endpoints | High | 5 | W6 | BE-011 | Multiple methods
☐ | BE-013 | Payment Gateway | Integrate Stripe/PayPal/VNPay | High | 6 | W6 | BE-012 | Sandbox testing
☐ | BE-014 | API - Surcharge | Surcharge calculation endpoints | Medium | 3 | W6 | BE-011 | Late return, damage
☐ | BE-015 | API - Promotion | Apply discount code | Medium | 3 | W6 | BE-011 | Validate expiry
☐ | BE-016 | Email Service | Setup email service (SendGrid/SES) | High | 4 | W6 | BE-001 | Booking confirmation
☐ | BE-017 | Models - SEO | Create models for 5 SEO tables | High | 3 | W7 | BE-003 | Blog, Review, Page
☐ | BE-018 | API - Blog | Blog CRUD endpoints | High | 4 | W7 | BE-017 | Rich text editor support
☐ | BE-019 | API - Review | Review submission, approval | High | 4 | W7 | BE-017 | Rating calculation
☐ | BE-020 | API - Page | Static pages endpoints | Medium | 2 | W7 | BE-017 | FAQ, About, Contact
☐ | BE-021 | SEO URLs | Slug generation, uniqueness check | Medium | 3 | W7 | BE-020 | Auto-generate from title
☐ | BE-022 | Image Upload | Setup S3/Cloudinary for images | High | 4 | W7 | BE-001 | Multiple images
☐ | BE-023 | Search API | Full-text search for vehicles, blogs | Medium | 5 | W7 | BE-021 | Elasticsearch optional
☐ | BE-024 | Models - Marketing | Create models for 6 marketing tables | High | 3 | W8 | BE-003 | Notification, Loyalty
☐ | BE-025 | API - Notification | Notification CRUD, mark as read | Medium | 3 | W8 | BE-024 | Real-time optional
☐ | BE-026 | SMS Service | Setup Twilio/AWS SNS | Medium | 3 | W8 | BE-016 | Booking SMS
☐ | BE-027 | API - Loyalty | Loyalty points earn/redeem | Medium | 5 | W8 | BE-024 | Transaction history
☐ | BE-028 | API - Campaign | Marketing campaign endpoints | Low | 4 | W8 | BE-024 | Send to segment
☐ | BE-029 | Models - Enterprise | Create models for 6 enterprise tables | High | 3 | W8 | BE-003 | Tenant, Partner
☐ | BE-030 | Multi-tenant Logic | Isolate data by TenantID | High | 6 | W8 | BE-029 | Critical for SaaS
☐ | BE-031 | API - Pricing Rule | Dynamic pricing calculation | Medium | 5 | W8 | BE-029 | Weekend, holiday pricing
☐ | BE-032 | API Documentation | Generate Swagger/OpenAPI docs | High | 4 | W8 | BE-031 | All endpoints
☐ | BE-033 | Error Handling | Standardize error responses | High | 3 | W8 | BE-001 | HTTP status codes
☐ | BE-034 | Logging | Setup Winston/Log4j | Medium | 2 | W8 | BE-001 | Info, error, debug
☐ | BE-035 | Rate Limiting | Prevent abuse | Medium | 2 | W8 | BE-001 | 100 req/min per IP
☐ | BE-036 | Unit Tests | Write tests for all endpoints | High | 8 | W8 | BE-035 | Jest/JUnit
☐ | BE-037 | Integration Tests | Test with real DB | High | 6 | W8 | BE-036 | Test DB setup
☐ | BE-038 | API Performance | Load testing (100 concurrent users) | Medium | 4 | W8 | BE-037 | JMeter/k6

## 🎨 Phase 3 Frontend
PHASE 3: FRONTEND DEVELOPMENT
Duration: 4 weeks ¦ Tech: React/Vue/Angular
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | FE-001 | Project Setup | Create React/Vue project | High | 2 | W9 | BE-038 | CRA or Vite
☐ | FE-002 | UI Library | Setup Ant Design/Material UI | High | 2 | W9 | FE-001 | Component library
☐ | FE-003 | Routing | Setup React Router/Vue Router | High | 2 | W9 | FE-001 | Protected routes
☐ | FE-004 | State Management | Setup Redux/Vuex/Zustand | High | 3 | W9 | FE-001 | Global state
☐ | FE-005 | API Integration | Setup Axios, API client | High | 3 | W9 | FE-001 | Base URL, interceptors
☐ | FE-006 | Auth Pages | Login, Register, Forgot Password | High | 6 | W9 | FE-005 | Form validation
☐ | FE-007 | Admin Layout | Sidebar, Header, Footer | High | 4 | W9 | FE-002 | Responsive
☐ | FE-008 | Dashboard | Admin dashboard with stats | High | 6 | W9 | FE-007 | Charts
☐ | FE-009 | Vehicle List | Table with filters, pagination | High | 4 | W9 | FE-007 | Search, sort
☐ | FE-010 | Vehicle CRUD | Create, Edit, Delete vehicle | High | 6 | W9 | FE-009 | Image upload
☐ | FE-011 | Customer List | Customer management table | High | 3 | W10 | FE-007 | Filters
☐ | FE-012 | Customer Detail | View/Edit customer profile | High | 3 | W10 | FE-011 | Booking history
☐ | FE-013 | Booking Calendar | Calendar view of bookings | High | 6 | W10 | FE-007 | FullCalendar.js
☐ | FE-014 | Booking Form | Create booking form | High | 6 | W10 | FE-013 | Date picker, validation
☐ | FE-015 | Booking Detail | View booking details | Medium | 4 | W10 | FE-014 | Timeline
☐ | FE-016 | Invoice Page | Generate and print invoice | High | 5 | W10 | FE-015 | PDF export
☐ | FE-017 | Payment Processing | Payment form UI | High | 4 | W10 | FE-016 | Payment gateway
☐ | FE-018 | Handover Form | Vehicle handover checklist | Medium | 4 | W10 | FE-015 | Photo upload
☐ | FE-019 | Return Form | Vehicle return report | Medium | 4 | W10 | FE-018 | Damage notes
☐ | FE-020 | Customer Portal | Separate customer interface | High | 4 | W11 | FE-001 | Different layout
☐ | FE-021 | Home Page | Landing page with search | High | 6 | W11 | FE-020 | Hero, features
☐ | FE-022 | Vehicle Catalog | Browse vehicles with filters | High | 6 | W11 | FE-021 | Grid/List view
☐ | FE-023 | Vehicle Detail | Vehicle detail page | High | 5 | W11 | FE-022 | Image gallery, specs
☐ | FE-024 | Booking Flow | Multi-step booking wizard | High | 8 | W11 | FE-023 | 4 steps
☐ | FE-025 | My Profile | Customer profile page | Medium | 3 | W11 | FE-020 | Edit info
☐ | FE-026 | My Bookings | Booking history and status | Medium | 4 | W11 | FE-025 | Active/Past
☐ | FE-027 | Write Review | Submit review form | Medium | 3 | W11 | FE-026 | Star rating
☐ | FE-028 | Loyalty Points | View points and rewards | Low | 3 | W11 | FE-025 | Transaction history
☐ | FE-029 | Blog List | Blog listing page | Medium | 3 | W12 | FE-021 | Categories, search
☐ | FE-030 | Blog Detail | Single blog post page | Medium | 3 | W12 | FE-029 | Rich text display
☐ | FE-031 | FAQ Page | FAQ accordion page | Low | 2 | W12 | FE-021 | Searchable
☐ | FE-032 | Contact Page | Contact form | Medium | 2 | W12 | FE-021 | Google Maps
☐ | FE-033 | Notifications | Notification dropdown | Medium | 4 | W12 | FE-007 | Real-time
☐ | FE-034 | Marketing Campaign | Campaign management UI | Low | 4 | W12 | FE-007 | Admin only
☐ | FE-035 | Reports Page | Charts and reports | Medium | 5 | W12 | FE-007 | Export Excel
☐ | FE-036 | Settings Page | System configuration | Low | 3 | W12 | FE-007 | Admin only
☐ | FE-037 | Responsive Design | Mobile optimization | High | 6 | W12 | FE-036 | All pages
☐ | FE-038 | Dark Mode | Theme switcher | Low | 3 | W12 | FE-037 | Optional
☐ | FE-039 | Loading States | Skeletons, spinners | Medium | 2 | W12 | FE-037 | UX improvement
☐ | FE-040 | Error Handling | Error pages, toast messages | Medium | 2 | W12 | FE-039 | 404, 500 pages

## 🧪 Phase 4 Testing
PHASE 4: TESTING & QA
Duration: 2 weeks
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | TS-001 | Unit Tests - Backend | Test all API endpoints | High | 8 | W13 | BE-038 | 80% coverage
☐ | TS-002 | Unit Tests - Frontend | Test React components | High | 6 | W13 | FE-040 | Jest, RTL
☐ | TS-003 | Integration Tests | Test API + DB together | High | 6 | W13 | TS-001 | Real scenarios
☐ | TS-004 | E2E Tests | Test complete user flows | High | 8 | W13 | TS-003 | Cypress/Playwright
☐ | TS-005 | Manual Testing | Test all features manually | High | 8 | W13 | TS-004 | Checklist
☐ | TS-006 | Bug Tracking | Log and prioritize bugs | High | 2 | W13 | TS-005 | Jira/GitHub Issues
☐ | TS-007 | Bug Fixing | Fix critical bugs | High | 10 | W13 | TS-006 | Priority 1
☐ | TS-008 | Performance Testing | Load test with 100+ concurrent users | High | 4 | W14 | TS-007 | JMeter
☐ | TS-009 | Security Testing | SQL injection, XSS, CSRF tests | High | 4 | W14 | TS-008 | OWASP checklist
☐ | TS-010 | Mobile Testing | Test on mobile devices | High | 4 | W14 | TS-009 | iOS, Android
☐ | TS-011 | Browser Testing | Test on Chrome, Safari, Firefox | Medium | 3 | W14 | TS-010 | Cross-browser
☐ | TS-012 | Accessibility | Test WCAG compliance | Medium | 3 | W14 | TS-011 | Screen readers
☐ | TS-013 | UAT | User acceptance testing | High | 6 | W14 | TS-012 | Real users
☐ | TS-014 | Final Bug Fixes | Fix remaining bugs | High | 8 | W14 | TS-013 | All priorities
☐ | TS-015 | Regression Testing | Retest everything after fixes | High | 4 | W14 | TS-014 | Full suite

## 🚀 Phase 5 Deployment
PHASE 5: DEPLOYMENT & LAUNCH
Duration: 2 weeks
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | DP-001 | Server Setup | Setup production server (AWS/Azure) | High | 4 | W15 | TS-015 | EC2/VM
☐ | DP-002 | Database Setup | Setup production database | High | 3 | W15 | DP-001 | RDS/Managed DB
☐ | DP-003 | Environment Vars | Configure production environment | High | 2 | W15 | DP-002 | .env files
☐ | DP-004 | SSL Certificate | Setup HTTPS | High | 2 | W15 | DP-001 | Let's Encrypt
☐ | DP-005 | Domain Setup | Configure domain and DNS | High | 2 | W15 | DP-004 | yourdomain.com
☐ | DP-006 | CI/CD Pipeline | Setup GitHub Actions/Jenkins | Medium | 4 | W15 | DP-001 | Auto deploy
☐ | DP-007 | Backup Strategy | Automated backups | High | 2 | W15 | DP-002 | Daily backups
☐ | DP-008 | Monitoring | Setup monitoring (Datadog/New Relic) | High | 3 | W15 | DP-001 | Alerts
☐ | DP-009 | Logging | Centralized logging | Medium | 2 | W15 | DP-008 | ELK stack
☐ | DP-010 | Documentation | Complete all documentation | High | 8 | W15 | TS-015 | User + Admin manuals
☐ | DP-011 | Staging Deploy | Deploy to staging environment | High | 2 | W16 | DP-010 | Final testing
☐ | DP-012 | Staging Testing | Final QA on staging | High | 4 | W16 | DP-011 | Smoke tests
☐ | DP-013 | Production Deploy | Deploy to production! | High | 3 | W16 | DP-012 | Zero downtime
☐ | DP-014 | Smoke Tests | Verify production is working | High | 2 | W16 | DP-013 | Critical paths
☐ | DP-015 | Performance Check | Check production performance | High | 2 | W16 | DP-014 | APM tools
☐ | DP-016 | Marketing Material | Prepare sales materials | High | 4 | W16 | DP-010 | Brochure, demo
☐ | DP-017 | Demo Video | Create product demo video | Medium | 4 | W16 | DP-016 | Screen recording
☐ | DP-018 | Launch Announcement | Announce product launch | High | 2 | W16 | DP-015 | Social media
☐ | DP-019 | Customer Support | Setup support system | Medium | 2 | W16 | DP-018 | Email/Chat
☐ | DP-020 | Celebration! | 🎉 Launch party | High | 4 | W16 | DP-019 | Team celebration!

## 💰 Resources & Budget
PROJECT RESOURCES & BUDGET
TEAM STRUCTURE
Role | Quantity | Rate (VND/month) | Duration (months) | Total Cost
Full-stack Developer (Senior) | 1 | 30000000 | 4 | 120000000
Full-stack Developer (Mid) | 2 | 20000000 | 4 | 160000000
UI/UX Designer | 1 | 15000000 | 2 | 30000000
QA Tester | 1 | 15000000 | 1 | 15000000
DevOps Engineer | 1 | 25000000 | 1 | 25000000
Project Manager | 1 | 25000000 | 4 | 100000000
|  |  | SUBTOTAL: | 450000000
INFRASTRUCTURE COSTS
Item | Provider | Cost (VND/month) | Duration (months) | Total Cost
Server (Production) | AWS EC2 t3.large | 2000000 | 4 | 8000000
Database (RDS) | AWS RDS MySQL | 3000000 | 4 | 12000000
Storage (S3) | AWS S3 | 500000 | 4 | 2000000
CDN | CloudFront | 500000 | 4 | 2000000
Email Service | SendGrid | 500000 | 4 | 2000000
SMS Service | Twilio | 1000000 | 4 | 4000000
Monitoring | Datadog | 1000000 | 4 | 4000000
Domain & SSL | Various | 500000 | 1 | 500000
|  |  | SUBTOTAL: | 34500000
OTHER COSTS
Item | Cost (VND)
Licenses (IDE, tools) | 5000000
Third-party APIs | 3000000
Marketing materials | 2000000
Contingency (10%) | 48450000
| SUBTOTAL: | 58450000
TOTAL PROJECT COST | 542950000 | VND
EXPECTED REVENUE | 500000000 | VND (Premium product sale)
NET PROFIT | -42950000 | VND
ROI | -7.91%