## 📊 Overview
CAR RENTAL MANAGEMENT SYSTEM
Modern Stack: NestJS + Next.js + MongoDB + Redis
Created: 2025-11-18
TECH STACK
Backend Framework: | NestJS 10.x | TypeScript, Modular architecture
Frontend Framework: | Next.js 14 | React 18, App Router, Server Components
Database: | MongoDB 7.x | NoSQL, Mongoose ODM
Cache: | Redis 7.x | In-memory caching, Session store
Storage: | AWS S3 / Cloudinary | Images, documents
Auth: | JWT + Passport | Access token + Refresh token
Validation: | class-validator | DTO validation
API Docs: | Swagger / OpenAPI | Auto-generated
Testing: | Jest + Supertest | Unit + Integration tests
Deployment: | Docker + Vercel | Backend Docker, Frontend Vercel
PROJECT INFORMATION
Total Collections: | 35 MongoDB collections | Full Premium Edition
Total Phases: | 5 phases | 16 weeks
Database Design: | MongoDB | Week 1-4
Backend (NestJS): | REST API | Week 5-8
Frontend (Next.js): | SSR/SSG | Week 9-12
Testing & QA: | All | Week 13-14
Deployment: | Production | Week 15-16
OVERALL PROGRESS
Phase | Status | Tasks | Completed | Progress % | Duration
Phase 1: MongoDB Design | Not Started | 35 | 0 |  | 4 weeks
Phase 2: NestJS API | Not Started | 40 | 0 |  | 4 weeks
Phase 3: Next.js UI | Not Started | 42 | 0 |  | 4 weeks
Phase 4: Testing | Not Started | 18 | 0 |  | 2 weeks
Phase 5: Deployment | Not Started | 15 | 0 |  | 2 weeks

## 🗄️ Phase 1 MongoDB
PHASE 1: MONGODB DATABASE DESIGN
Duration: 4 weeks ¦ Collections: 35 ¦ ODM: Mongoose
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | DB-001 | Install MongoDB | Setup MongoDB 7.x locally + MongoDB Compass | High | 2 | W1 | - | Or use MongoDB Atlas (cloud)
☐ | DB-002 | Design Schemas | Design 35 Mongoose schemas | High | 8 | W1 | DB-001 | Embedded vs Referenced
☐ | DB-003 | Core Collections (20) | Vehicle, Customer, Booking, Invoice... | High | 12 | W1 | DB-002 | Define indexes
☐ | DB-004 | Relationships | ObjectId references, populate strategy | High | 4 | W1 | DB-003 | One-to-Many, Many-to-Many
☐ | DB-005 | Validation Rules | Schema validation, required fields | High | 3 | W1 | DB-003 | Mongoose validators
☐ | DB-006 | Indexes - Basic | Create indexes for common queries | High | 3 | W1 | DB-005 | Single field indexes
☐ | DB-007 | Compound Indexes | Multi-field indexes for complex queries | High | 3 | W2 | DB-006 | Query optimization
☐ | DB-008 | Text Indexes | Full-text search for blogs, vehicles | Medium | 2 | W2 | DB-007 | Weighted text search
☐ | DB-009 | Geospatial Index | Branch location search (2dsphere) | Medium | 2 | W2 | DB-007 | Near query support
☐ | DB-010 | TTL Index | Auto-expire sessions, notifications | Low | 1 | W2 | DB-007 | expireAfterSeconds
☐ | DB-011 | Virtual Properties | Computed fields (fullName, age...) | Medium | 2 | W2 | DB-005 | Mongoose virtuals
☐ | DB-012 | Pre/Post Hooks | Middleware for save, update, delete | Medium | 3 | W2 | DB-005 | Hash passwords, audit
☐ | DB-013 | Plugins | Timestamps, soft delete, pagination | Medium | 2 | W2 | DB-012 | Reusable logic
☐ | DB-014 | Sample Data Script | Seed 100+ documents per collection | High | 4 | W2 | DB-013 | faker.js
☐ | DB-015 | Test Relationships | Test populate() and aggregations | High | 3 | W2 | DB-014 | Verify data integrity
☐ | DB-016 | SEO Collections (5) | BlogPost, BlogCategory, Page, Review, SeoRedirect | High | 4 | W3 | DB-005 | Slug uniqueness
☐ | DB-017 | Update Core Schemas | Add SEO fields (slug, metaTitle...) | High | 3 | W3 | DB-016 | Vehicle, Category, Branch
☐ | DB-018 | Embedded Documents | DepositDetail inside Deposit | Medium | 2 | W3 | DB-002 | Denormalization
☐ | DB-019 | Array Fields | Images[], accessories[], features[] | Medium | 2 | W3 | DB-018 | Document arrays
☐ | DB-020 | Aggregation Pipelines | Revenue reports, analytics | High | 4 | W3 | DB-015 | $match, $group, $project
☐ | DB-021 | Lookups | JOIN-like operations ($lookup) | Medium | 3 | W3 | DB-020 | Left outer join
☐ | DB-022 | Sample SEO Data | Insert 50 blog posts, 100 reviews | Medium | 3 | W3 | DB-021 | Rich content
☐ | DB-023 | Marketing Collections (6) | Notification, Segment, Campaign, Loyalty... | High | 4 | W4 | DB-005 | JSON fields
☐ | DB-024 | Enterprise Collections (6) | Tenant, Plan, PricingRule, Corporate... | High | 4 | W4 | DB-005 | Multi-tenant design
☐ | DB-025 | Update Customer | Add loyaltyPoints, membershipTier | Medium | 1 | W4 | DB-023 | Loyalty system
☐ | DB-026 | Change Streams | Watch for real-time changes | Low | 2 | W4 | DB-024 | MongoDB 4.0+ feature
☐ | DB-027 | Transactions | ACID for booking + payment | High | 3 | W4 | DB-024 | Multi-document txn
☐ | DB-028 | Backup Strategy | mongodump automation | High | 2 | W4 | DB-027 | Daily backups
☐ | DB-029 | Query Optimization | Analyze slow queries with explain() | High | 3 | W4 | DB-020 | Add missing indexes
☐ | DB-030 | Data Migration Script | Import from SQL if needed | Low | 4 | W4 | DB-002 | Optional
☐ | DB-031 | Schema Documentation | Document all 35 schemas | Medium | 3 | W4 | DB-030 | README.md
☐ | DB-032 | Atlas Setup (Optional) | Setup MongoDB Atlas cluster | Medium | 2 | W4 | DB-001 | Cloud database
☐ | DB-033 | Performance Baseline | Test with 10k documents | High | 2 | W4 | DB-029 | Benchmark queries
☐ | DB-034 | Security | Enable auth, create users, roles | High | 2 | W4 | DB-033 | RBAC
☐ | DB-035 | Connection Pooling | Configure pool size | Medium | 1 | W4 | DB-034 | maxPoolSize: 10

## ⚙️ Phase 2 NestJS
PHASE 2: NESTJS BACKEND API
Duration: 4 weeks ¦ Framework: NestJS 10 + TypeScript
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | BE-001 | Install NestJS CLI | npm i -g @nestjs/cli | High | 1 | W5 | DB-035 | Latest version
☐ | BE-002 | Create Project | nest new car-rental-api | High | 1 | W5 | BE-001 | Choose npm/yarn/pnpm
☐ | BE-003 | Project Structure | Setup modules (auth, vehicle, booking...) | High | 3 | W5 | BE-002 | Feature-based modules
☐ | BE-004 | MongoDB Connection | @nestjs/mongoose + mongoose | High | 2 | W5 | BE-003 | MongooseModule.forRoot()
☐ | BE-005 | Environment Config | @nestjs/config + .env files | High | 2 | W5 | BE-002 | ConfigModule
☐ | BE-006 | Mongoose Schemas | Create 20 core schemas | High | 8 | W5 | BE-004 | @Schema() decorator
☐ | BE-007 | DTOs | Create DTOs with class-validator | High | 6 | W5 | BE-006 | CreateVehicleDto, UpdateVehicleDto
☐ | BE-008 | Auth Module | JWT strategy + Passport | High | 6 | W5 | BE-005 | @nestjs/jwt, @nestjs/passport
☐ | BE-009 | Guards | JwtAuthGuard, RolesGuard | High | 3 | W5 | BE-008 | @UseGuards() decorator
☐ | BE-010 | Decorators | Custom decorators (@CurrentUser) | Medium | 2 | W5 | BE-009 | createParamDecorator()
☐ | BE-011 | Vehicle Module | CRUD endpoints | High | 4 | W6 | BE-006 | VehicleController + VehicleService
☐ | BE-012 | Customer Module | CRUD endpoints | High | 3 | W6 | BE-006 | CustomerController + CustomerService
☐ | BE-013 | Booking Module | Create, update, cancel booking | High | 6 | W6 | BE-012 | Complex business logic
☐ | BE-014 | Validation Pipes | ValidationPipe for all DTOs | High | 2 | W6 | BE-007 | Global pipe
☐ | BE-015 | Exception Filters | HttpExceptionFilter | High | 2 | W6 | BE-014 | Consistent error format
☐ | BE-016 | Interceptors | LoggingInterceptor, TransformInterceptor | Medium | 2 | W6 | BE-015 | AOP pattern
☐ | BE-017 | Invoice Module | Generate invoice, calculate total | High | 4 | W6 | BE-013 | InvoiceService
☐ | BE-018 | Payment Integration | Stripe/PayPal SDK | High | 5 | W6 | BE-017 | Webhook handling
☐ | BE-019 | Surcharge Service | Calculate late fees, damage fees | Medium | 3 | W6 | BE-017 | Business rules
☐ | BE-020 | Email Service | @nestjs-modules/mailer | High | 3 | W6 | BE-005 | SendGrid/Nodemailer
☐ | BE-021 | Redis Setup | @nestjs/cache-manager + redis | High | 2 | W7 | BE-005 | CacheModule
☐ | BE-022 | Caching Strategy | Cache vehicles, prices | High | 3 | W7 | BE-021 | @CacheTTL() decorator
☐ | BE-023 | Session Store | Redis session for auth | Medium | 2 | W7 | BE-021 | express-session + connect-redis
☐ | BE-024 | Blog Module | CRUD for blog posts | High | 4 | W7 | BE-006 | Rich text support
☐ | BE-025 | Review Module | Submit, approve reviews | High | 4 | W7 | BE-013 | Rating calculation
☐ | BE-026 | Page Module | Static pages (FAQ, About) | Medium | 2 | W7 | BE-024 | CMS-like
☐ | BE-027 | Search Service | Text search across collections | Medium | 4 | W7 | BE-026 | MongoDB $text
☐ | BE-028 | File Upload | Multer + S3/Cloudinary | High | 4 | W7 | BE-005 | @nestjs/platform-express
☐ | BE-029 | Image Processing | Sharp for resize | Medium | 2 | W7 | BE-028 | Thumbnails
☐ | BE-030 | Notification Module | Email, SMS, Push notifications | Medium | 4 | W8 | BE-020 | Queue with Bull
☐ | BE-031 | Queue Processing | @nestjs/bull + Redis | Medium | 3 | W8 | BE-030 | Background jobs
☐ | BE-032 | Loyalty Module | Points earn/redeem | Medium | 4 | W8 | BE-006 | Transaction history
☐ | BE-033 | Campaign Module | Marketing campaigns | Low | 3 | W8 | BE-030 | Send to segments
☐ | BE-034 | Multi-tenant Logic | Tenant isolation middleware | High | 5 | W8 | BE-009 | TenantContext
☐ | BE-035 | Pricing Rule Engine | Dynamic pricing calculation | Medium | 4 | W8 | BE-011 | Strategy pattern
☐ | BE-036 | Swagger Documentation | @nestjs/swagger | High | 3 | W8 | BE-035 | OpenAPI 3.0
☐ | BE-037 | API Versioning | v1 routes | Medium | 2 | W8 | BE-036 | VERSION_NEUTRAL
☐ | BE-038 | Rate Limiting | @nestjs/throttler | Medium | 2 | W8 | BE-037 | 100 req/min
☐ | BE-039 | Helmet Security | helmet + CORS | High | 1 | W8 | BE-038 | Security headers
☐ | BE-040 | Unit Tests | Jest tests for services | High | 8 | W8 | BE-039 | 80% coverage

## 🎨 Phase 3 Next.js
PHASE 3: NEXT.JS FRONTEND
Duration: 4 weeks ¦ Framework: Next.js 14 + React 18 + App Router
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | FE-001 | Create Next.js App | npx create-next-app@latest | High | 1 | W9 | BE-040 | Choose TypeScript, App Router, Tailwind
☐ | FE-002 | Project Structure | Setup app/ directory structure | High | 2 | W9 | FE-001 | app/api, app/(admin), app/(customer)
☐ | FE-003 | UI Library | Install shadcn/ui + Tailwind | High | 2 | W9 | FE-002 | Radix UI primitives
☐ | FE-004 | Auth Setup | NextAuth.js v5 (Auth.js) | High | 4 | W9 | FE-003 | JWT provider
☐ | FE-005 | API Client | Axios + React Query (TanStack) | High | 3 | W9 | FE-001 | Data fetching & caching
☐ | FE-006 | State Management | Zustand (lightweight) | Medium | 2 | W9 | FE-005 | Global state
☐ | FE-007 | Layout Components | AdminLayout, CustomerLayout | High | 4 | W9 | FE-003 | Nested layouts
☐ | FE-008 | Auth Pages | Login, Register (Server Components) | High | 5 | W9 | FE-004 | Form actions
☐ | FE-009 | Dashboard Page | Admin dashboard with stats | High | 6 | W9 | FE-007 | Recharts for charts
☐ | FE-010 | Vehicle List | DataTable with filters (Server Component) | High | 5 | W9 | FE-009 | @tanstack/react-table
☐ | FE-011 | Vehicle CRUD | Create/Edit vehicle pages | High | 6 | W10 | FE-010 | React Hook Form + Zod
☐ | FE-012 | Image Upload | Client-side upload to S3/Cloudinary | High | 4 | W10 | FE-011 | react-dropzone
☐ | FE-013 | Customer List | Customer management table | High | 3 | W10 | FE-007 | Pagination, search
☐ | FE-014 | Booking Calendar | FullCalendar integration | High | 6 | W10 | FE-013 | @fullcalendar/react
☐ | FE-015 | Booking Form | Multi-step wizard | High | 7 | W10 | FE-014 | react-hook-form steps
☐ | FE-016 | Invoice Page | Invoice preview + print | High | 4 | W10 | FE-015 | react-to-print
☐ | FE-017 | Payment Integration | Stripe Elements | High | 5 | W10 | FE-016 | @stripe/react-stripe-js
☐ | FE-018 | Handover Checklist | Vehicle inspection form | Medium | 4 | W10 | FE-015 | Photo capture
☐ | FE-019 | Customer Landing | Home page (SSG) | High | 5 | W11 | FE-001 | Hero, features, testimonials
☐ | FE-020 | Vehicle Catalog | Browse vehicles (SSG/ISR) | High | 6 | W11 | FE-019 | generateStaticParams()
☐ | FE-021 | Vehicle Detail | Dynamic route [vehicleId] | High | 5 | W11 | FE-020 | Image gallery, specs
☐ | FE-022 | Search & Filters | Advanced search UI | High | 5 | W11 | FE-020 | URL params
☐ | FE-023 | Booking Wizard | 4-step booking flow | High | 8 | W11 | FE-021 | Date picker, vehicle select
☐ | FE-024 | My Profile | Customer profile page | Medium | 3 | W11 | FE-019 | Edit info
☐ | FE-025 | My Bookings | Booking history | Medium | 4 | W11 | FE-024 | Active/Past tabs
☐ | FE-026 | Review Form | Submit review with stars | Medium | 3 | W11 | FE-025 | react-stars
☐ | FE-027 | Loyalty Dashboard | Points, rewards, history | Low | 3 | W11 | FE-024 | Tier badges
☐ | FE-028 | Notifications | Real-time notifications | Medium | 4 | W11 | FE-024 | Socket.io or Polling
☐ | FE-029 | Blog Pages | Blog list + single post (MDX) | Medium | 4 | W12 | FE-019 | next-mdx-remote
☐ | FE-030 | SEO Optimization | Metadata API, sitemap, robots.txt | High | 4 | W12 | FE-029 | generateMetadata()
☐ | FE-031 | FAQ Page | Accordion with search | Low | 2 | W12 | FE-019 | Collapsible
☐ | FE-032 | Contact Page | Contact form + Google Maps | Medium | 3 | W12 | FE-019 | react-leaflet
☐ | FE-033 | Admin Reports | Charts and analytics | Medium | 5 | W12 | FE-009 | Recharts
☐ | FE-034 | Settings Page | System config UI | Low | 3 | W12 | FE-007 | Admin only
☐ | FE-035 | Dark Mode | next-themes | Low | 2 | W12 | FE-003 | Toggle theme
☐ | FE-036 | Loading States | Suspense + loading.tsx | High | 3 | W12 | FE-035 | Skeletons
☐ | FE-037 | Error Handling | error.tsx + not-found.tsx | High | 2 | W12 | FE-036 | Error boundaries
☐ | FE-038 | Responsive Design | Mobile-first optimization | High | 6 | W12 | FE-037 | All pages
☐ | FE-039 | Performance | Image optimization, lazy loading | High | 4 | W12 | FE-038 | next/image
☐ | FE-040 | Internationalization | next-intl (optional) | Low | 4 | W12 | FE-039 | Multi-language
☐ | FE-041 | Analytics | Google Analytics 4 | Medium | 2 | W12 | FE-040 | gtag.js
☐ | FE-042 | PWA Support | next-pwa | Low | 3 | W12 | FE-041 | Offline support

## 🧪 Phase 4 Testing
PHASE 4: TESTING & QA
Duration: 2 weeks ¦ Tools: Jest + Supertest + Playwright
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | TS-001 | Unit Tests - Backend | Test NestJS services | High | 8 | W13 | BE-040 | Jest + @nestjs/testing
☐ | TS-002 | Unit Tests - Frontend | Test React components | High | 6 | W13 | FE-042 | Jest + React Testing Library
☐ | TS-003 | E2E Tests - Backend | Test API endpoints | High | 6 | W13 | TS-001 | Supertest
☐ | TS-004 | E2E Tests - Frontend | Test user flows | High | 8 | W13 | TS-002 | Playwright
☐ | TS-005 | Integration Tests | Test API + DB together | High | 5 | W13 | TS-003 | Test MongoDB
☐ | TS-006 | Coverage Report | Generate coverage reports | Medium | 2 | W13 | TS-005 | c8 or nyc
☐ | TS-007 | Manual Testing | Test all features manually | High | 8 | W13 | TS-006 | Checklist
☐ | TS-008 | Bug Tracking | Log bugs in GitHub Issues | High | 2 | W13 | TS-007 | Priority labels
☐ | TS-009 | Bug Fixing - P1 | Fix critical bugs | High | 10 | W13 | TS-008 | Blockers
☐ | TS-010 | Performance Testing | Load test with k6 | High | 4 | W14 | TS-009 | 100+ concurrent users
☐ | TS-011 | Lighthouse Audit | Test Next.js performance | High | 3 | W14 | TS-010 | Score > 90
☐ | TS-012 | Security Testing | OWASP ZAP scan | High | 4 | W14 | TS-011 | SQL injection, XSS
☐ | TS-013 | Accessibility | axe-core testing | Medium | 3 | W14 | TS-012 | WCAG 2.1 AA
☐ | TS-014 | Cross-browser | Test on Chrome, Safari, Firefox | Medium | 3 | W14 | TS-013 | BrowserStack
☐ | TS-015 | Mobile Testing | Test on iOS & Android | High | 4 | W14 | TS-014 | Responsive
☐ | TS-016 | UAT | User acceptance testing | High | 6 | W14 | TS-015 | Real users
☐ | TS-017 | Bug Fixing - All | Fix remaining bugs | High | 8 | W14 | TS-016 | All priorities
☐ | TS-018 | Regression Testing | Retest everything | High | 4 | W14 | TS-017 | Full suite

## 🚀 Phase 5 Deployment
PHASE 5: DEPLOYMENT & LAUNCH
Duration: 2 weeks ¦ Backend: Docker ¦ Frontend: Vercel
✓ | Task ID | Task Name | Description | Priority | Hours | Week | Dependencies | Notes
☐ | DP-001 | Dockerfile Backend | Create Dockerfile for NestJS | High | 2 | W15 | TS-018 | Multi-stage build
☐ | DP-002 | Docker Compose | MongoDB + Redis + NestJS | High | 2 | W15 | DP-001 | Local dev environment
☐ | DP-003 | MongoDB Atlas | Setup production database | High | 2 | W15 | DP-002 | M10 cluster
☐ | DP-004 | Redis Cloud | Setup Redis production | Medium | 1 | W15 | DP-003 | Redis Labs
☐ | DP-005 | AWS/DigitalOcean | Setup server for backend | High | 3 | W15 | DP-004 | EC2/Droplet
☐ | DP-006 | Docker Deploy | Deploy backend container | High | 2 | W15 | DP-005 | docker-compose up
☐ | DP-007 | Nginx Reverse Proxy | Setup Nginx | High | 2 | W15 | DP-006 | SSL + load balancing
☐ | DP-008 | SSL Certificate | Let's Encrypt + Certbot | High | 1 | W15 | DP-007 | Auto-renew
☐ | DP-009 | Vercel Deploy | Deploy Next.js to Vercel | High | 1 | W15 | TS-018 | Connect GitHub
☐ | DP-010 | Environment Vars | Configure all env variables | High | 2 | W15 | DP-009 | Vercel dashboard
☐ | DP-011 | Domain Setup | Configure custom domain | High | 1 | W15 | DP-010 | DNS records
☐ | DP-012 | CI/CD Pipeline | GitHub Actions | High | 4 | W15 | DP-011 | Auto deploy on push
☐ | DP-013 | Monitoring | Setup PM2 + Sentry | High | 3 | W15 | DP-012 | Error tracking
☐ | DP-014 | Logging | Winston + Logtail | Medium | 2 | W15 | DP-013 | Centralized logs
☐ | DP-015 | Backup Strategy | Automated MongoDB backups | High | 2 | W15 | DP-003 | Daily snapshots
☐ | DP-016 | Staging Tests | Final QA on staging | High | 4 | W16 | DP-015 | Smoke tests
☐ | DP-017 | Performance Check | Verify production speed | High | 2 | W16 | DP-016 | Lighthouse
☐ | DP-018 | Security Audit | Final security review | High | 2 | W16 | DP-017 | Penetration test
☐ | DP-019 | Documentation | Complete all docs | High | 6 | W16 | DP-018 | API + User manuals
☐ | DP-020 | Demo Video | Record product demo | Medium | 3 | W16 | DP-019 | Loom or OBS
☐ | DP-021 | Marketing Site | Landing page for product | High | 4 | W16 | DP-020 | Features, pricing
☐ | DP-022 | Customer Support | Setup support system | Medium | 2 | W16 | DP-021 | Email + Chat
☐ | DP-023 | Analytics Setup | Google Analytics + Mixpanel | Medium | 2 | W16 | DP-022 | Track conversions
☐ | DP-024 | Production Deploy | 🚀 LAUNCH! | High | 3 | W16 | DP-023 | Go live!
☐ | DP-025 | Post-launch Monitor | 24/7 monitoring first week | High | 8 | W16 | DP-024 | Fix issues ASAP

## 💰 Resources & Budget
RESOURCES & BUDGET (MODERN STACK)
TECH STACK DETAILS
Category | Technology | Version | Purpose
Backend | NestJS | 10.x | REST API framework
| Mongoose | 8.x | MongoDB ODM
| Passport JWT | latest | Authentication
| class-validator | latest | DTO validation
| Bull | latest | Job queues
Frontend | Next.js | 14.x | React framework
| React | 18.x | UI library
| TypeScript | 5.x | Type safety
| Tailwind CSS | 3.x | Styling
| shadcn/ui | latest | Component library
| React Query | latest | Data fetching
| Zustand | latest | State management
Database | MongoDB | 7.x | NoSQL database
| MongoDB Atlas | - | Cloud hosting
Cache | Redis | 7.x | Caching & sessions
| Redis Cloud | - | Cloud hosting
Storage | AWS S3 | - | File storage
| Cloudinary | - | Image CDN
Testing | Jest | latest | Unit tests
| Supertest | latest | API tests
| Playwright | latest | E2E tests
Deploy | Docker | latest | Backend container
| Vercel | - | Frontend hosting
| GitHub Actions | - | CI/CD
TEAM & BUDGET
Role | Qty | Rate (VND/mo) | Months | Total
Full-stack (Senior) | 1 | 35000000 | 4
Full-stack (Mid) | 2 | 22000000 | 4
UI/UX Designer | 1 | 15000000 | 2
QA Engineer | 1 | 18000000 | 1
DevOps | 1 | 25000000 | 1
PM | 1 | 25000000 | 4
SUBTOTAL:
INFRASTRUCTURE (MODERN STACK)
Service | Provider | Cost (VND/mo) | Months | Total
Backend Server | DigitalOcean Droplet | 1500000 | 4
MongoDB Atlas | M10 cluster | 2000000 | 4
Redis Cloud | 30MB plan | 500000 | 4
S3 Storage | AWS | 300000 | 4
Cloudinary | Plus plan | 700000 | 4
Vercel | Pro plan | 500000 | 4
Domain + SSL | Various | 300000 | 1
Sentry | Developer plan | 500000 | 4
SUBTOTAL:
TOTAL PROJECT COST |  | VND
EXPECTED REVENUE | 500000000 | VND
NET PROFIT
ROI